## Dashboard
NEXS Website Development Build Plan v5.2
Project | NEXS Premium Automotive Film Website
Version | v5.2
Build Rule | No public pricing anywhere
Theme | White / soft grey / black panels / restrained red accent
Core Campaign | Think New. Think NEXS.
Product Scope | 12 film options: Clear 4, Matte 3, Color 5
Final Stack | Next.js + React + TypeScript + Tailwind CSS + Sanity CMS
Development KPIs
Total Tasks | P0 Tasks | P1 Tasks | Build Days | Open Decisions | Launch Blockers | Forms | Core Pages
84 | 54 | 28 | 78 | 2 | 0 | 4 | 9
Formula-driven | Highest priority | Important | Estimate | Need owner | Must resolve | Quote / Contact / Dealer / Installer | Home + product + brand pages
Phase | Task Count | Estimated Days
Sprint 0 - Setup | 14 | 9
Sprint 1 - UI Foundation | 13 | 14.25
Sprint 2 - Core Pages | 10 | 9.75
Sprint 3 - Product System | 14 | 15
Sprint 4 - Forms CMS Analytics | 17 | 17.25
Sprint 5 - QA Launch | 16 | 12.75

## Backlog
ID | Phase | Area | Task | Deliverable | Priority | Owner | Est. Days | Status | Dependency | Acceptance Criteria
DEV-001 | Sprint 0 - Setup | Project | Create project repository and branch strategy | Git repository with main/develop branches | P0 | Project Lead | 0.5 | Not Started |  | Repository created; access granted
DEV-002 | Sprint 0 - Setup | Project | Confirm final implementation stack | Next.js + Sanity CMS stack decision recorded | P0 | Project Lead | 0.5 | Locked v5.2 |  | Stack locked: Next.js / React / TypeScript / Tailwind CSS + Sanity CMS + GitHub Actions CI/CD
DEV-003 | Sprint 0 - Setup | Infrastructure | Prepare staging and production environments | Staging/prod deployment targets | P0 | Developer | 1 | Not Started | DEV-002 | Staging URL accessible
DEV-004 | Sprint 0 - Setup | Infrastructure | Configure environment variables and secrets process | Secrets template and environment checklist | P0 | Developer | 0.5 | Not Started | DEV-003 | No secrets committed to repository
DEV-005 | Sprint 0 - Setup | Design | Import v4 design tokens into codebase | CSS variables / theme config | P0 | Developer | 0.75 | Not Started |  | Colors, spacing and radius match v4 token file
DEV-006 | Sprint 0 - Setup | Design | Set up font loading for English and Thai | Font stack and fallback rules | P0 | Developer | 0.5 | Not Started |  | Thai text renders cleanly on desktop/mobile
DEV-007 | Sprint 0 - Setup | Content | Load Step 1 final copy into content inventory | Content source file / CMS seed | P0 | Content Admin | 1 | Not Started |  | No AI placeholder copy visible
DEV-008 | Sprint 0 - Setup | Content | Confirm no public pricing rule across CMS fields | Pricing field exclusion rule | P0 | Project Lead | 0.5 | Not Started |  | Public templates cannot render prices
DEV-009 | Sprint 0 - Setup | Assets | Map Step 3 asset IDs to route usage | P0 AI-render asset map document | P0 | Designer | 1 | Not Started |  | P0 images assigned to pages; launch source set to AI render where image asset is photo/render-based
DEV-010 | Sprint 0 - Setup | QA | Create QA issue tracker and acceptance workflow | Issue tracker with owners/status | P1 | QA | 0.5 | Not Started |  | All defects logged with owner and severity
DEV-011 | Sprint 1 - UI Foundation | UI Foundation | Implement global layout shell | Header, main, footer layout | P0 | Developer | 1.5 | Not Started | DEV-005 | Layout matches visual reference
DEV-012 | Sprint 1 - UI Foundation | UI Foundation | Build responsive navigation | Desktop nav + mobile drawer | P0 | Developer | 1.5 | Not Started | DEV-011 | Navigation works at 390/768/1440 widths
DEV-013 | Sprint 1 - UI Foundation | UI Foundation | Build button system | Primary, secondary, text, disabled states | P0 | Developer | 0.75 | Not Started | DEV-005 | CTA styles consistent across pages
DEV-014 | Sprint 1 - UI Foundation | UI Foundation | Build typography scale | H1/H2/body/caption classes | P0 | Developer | 0.75 | Not Started | DEV-006 | No overflow with Thai/English text
DEV-015 | Sprint 1 - UI Foundation | UI Foundation | Build hero component | Campaign, headline, Thai copy, CTA, image area | P0 | Developer | 1.5 | Not Started | DEV-013 | Homepage hero matches approved white theme
DEV-016 | Sprint 1 - UI Foundation | UI Foundation | Build product tier card component | Cards for Begin/Prime/Pro/Ultimate tiers | P0 | Developer | 1.25 | Not Started | DEV-013 | Supports 4, 3 and 5-tier layouts
DEV-017 | Sprint 1 - UI Foundation | UI Foundation | Build comparison table component | Responsive table with sticky first column optional | P1 | Developer | 1.25 | Not Started |  | Readable on mobile
DEV-018 | Sprint 1 - UI Foundation | UI Foundation | Build quote block component | Black panel with controlled red accents | P1 | Developer | 0.75 | Not Started | DEV-005 | Uses black panel only in approved sections
DEV-019 | Sprint 1 - UI Foundation | UI Foundation | Build technology card grid | Layer / TPU / self-healing / adhesive cards | P1 | Developer | 1 | Not Started |  | Cards wrap correctly
DEV-020 | Sprint 1 - UI Foundation | UI Foundation | Build FAQ accordion | Accessible accordion interactions | P1 | Developer | 1 | Not Started |  | Keyboard and screen reader accessible
DEV-021 | Sprint 1 - UI Foundation | UI Foundation | Build gallery and image block components | Responsive image cards/carousel | P1 | Developer | 1 | Not Started | DEV-009 | Images lazy-loaded and cropped correctly
DEV-022 | Sprint 1 - UI Foundation | UI Foundation | Build form component library | Input/select/textarea/checkbox/error/success | P0 | Developer | 1.25 | Not Started | DEV-013 | Validation states visible
DEV-023 | Sprint 1 - UI Foundation | UI Foundation | Build footer | Navigation, contact, social, legal | P1 | Developer | 0.75 | Not Started |  | Footer consistent across routes
DEV-024 | Sprint 2 - Core Pages | Homepage | Build homepage section 01 hero | Hero section with final campaign and CTA | P0 | Developer | 1.25 | Not Started | DEV-015 | Campaign and Thai hero are exact
DEV-025 | Sprint 2 - Core Pages | Homepage | Build homepage product system overview | Clear/Matte/Color summary cards | P0 | Developer | 1 | Not Started | DEV-016 | Shows 12 film options without pricing
DEV-026 | Sprint 2 - Core Pages | Homepage | Build homepage NEXS standard section | Four brand pillars | P1 | Developer | 0.75 | Not Started |  | Brand language matches copy lock
DEV-027 | Sprint 2 - Core Pages | Homepage | Build homepage technology preview | Technology cards + CTA to technology page | P1 | Developer | 0.75 | Not Started | DEV-019 | CTA route works
DEV-028 | Sprint 2 - Core Pages | Homepage | Build homepage dealer CTA section | Professional installer CTA | P1 | Developer | 0.75 | Not Started | DEV-022 | Dealer CTA does not show prices
DEV-029 | Sprint 2 - Core Pages | About NEXS | Build About hero and story | Brand story sections | P1 | Developer | 1 | Not Started | DEV-015 | No old Shine and Shield language
DEV-030 | Sprint 2 - Core Pages | About NEXS | Build NEXS standard content blocks | Standard / surface / confidence content | P1 | Developer | 1 | Not Started | DEV-018 | Quote block appears as approved
DEV-031 | Sprint 2 - Core Pages | Technology | Build technology landing page | Layer stack, TPU, adhesive, self-healing sections | P1 | Developer | 1.5 | Not Started | DEV-019 | Technology content readable and visual
DEV-032 | Sprint 2 - Core Pages | FAQ | Build FAQ page | FAQ categories and accordions | P1 | Developer | 0.75 | Not Started | DEV-020 | FAQ schema-ready content structure
DEV-033 | Sprint 2 - Core Pages | Contact | Build contact page shell | Contact details, form, map placeholder | P0 | Developer | 1 | Not Started | DEV-022 | Contact form visible and no mock contact data
DEV-034 | Sprint 3 - Product System | Clear PPF | Build Clear PPF hero | Clear product hero with invisible concept | P0 | Developer | 1 | Not Started | DEV-015 | Headline exact; clear product scope displayed
DEV-035 | Sprint 3 - Product System | Clear PPF | Build 4-tier Clear PPF cards | Begin, Prime, Pro, Ultimate | P0 | Developer | 1.25 | Not Started | DEV-016 | Four cards rendered; no prices
DEV-036 | Sprint 3 - Product System | Clear PPF | Build Clear PPF comparison table | Public specs only | P0 | Developer | 1 | Not Started | DEV-017 | No internal cost/supplier fields
DEV-037 | Sprint 3 - Product System | Clear PPF | Build Clear PPF FAQ and CTA | FAQ plus Get a Quote | P1 | Developer | 0.75 | Not Started | DEV-020 | CTA tracked
DEV-038 | Sprint 3 - Product System | Matte PPF | Build Matte PPF hero | Matte positioning and final 3-tier structure | P0 | Developer | 1 | Not Started | DEV-015 | Matte Prime/Pro/Ultimate confirmed
DEV-039 | Sprint 3 - Product System | Matte PPF | Build 3-tier Matte PPF cards | Matte Prime, Matte Pro, Matte Ultimate | P0 | Developer | 1.25 | Not Started | DEV-016 | Mockup specs mapped from Clear tiers
DEV-040 | Sprint 3 - Product System | Matte PPF | Build Matte comparison table | Public spec table | P1 | Developer | 0.75 | Not Started | DEV-017 | Readable on mobile
DEV-041 | Sprint 3 - Product System | Color PPF | Build Color PPF hero | Color style/product positioning | P0 | Developer | 1 | Not Started | DEV-015 | Color structure reflects 5 tiers
DEV-042 | Sprint 3 - Product System | Color PPF | Build 5-tier Color PPF cards | Begin, Prime, Pro, Ultimate, Ultimate Carbon Fiber | P0 | Developer | 1.5 | Not Started | DEV-016 | Five cards rendered; carbon detail included
DEV-043 | Sprint 3 - Product System | Color PPF | Build color swatch/finish grid | Swatch gallery with finish labels | P1 | Developer | 1 | Not Started | DEV-021 | Does not imply unavailable colors
DEV-044 | Sprint 3 - Product System | Color PPF | Build color comparison table | Public specs only | P1 | Developer | 1 | Not Started | DEV-017 | No public pricing
DEV-045 | Sprint 3 - Product System | Compare | Build comparison page | All product groups + guide to choose | P1 | Developer | 1.5 | Not Started | DEV-017 | Clear, Matte, Color comparison usable
DEV-046 | Sprint 3 - Product System | Product Data | Create reusable product data schema | Data source for all cards/tables | P0 | Developer | 1 | Not Started | DEV-007 | Product content editable without template rewrites
DEV-047 | Sprint 3 - Product System | Product Data | Seed public product data | 12 options with locked names | P0 | Content Admin | 1 | Not Started | DEV-046 | Names and copy match v1.2 matrix
DEV-048 | Sprint 4 - Forms CMS Analytics | CMS | Implement content model: Pages | Editable page sections | P1 | Developer | 1 | Not Started | DEV-002 | Page content editable
DEV-049 | Sprint 4 - Forms CMS Analytics | CMS | Implement content model: Products | Product cards/specs with no price fields | P0 | Developer | 1.5 | Not Started | DEV-046 | CMS has no public price fields
DEV-050 | Sprint 4 - Forms CMS Analytics | CMS | Implement content model: FAQ | FAQ categories/questions | P1 | Developer | 0.75 | Not Started |  | FAQ editable
DEV-051 | Sprint 4 - Forms CMS Analytics | CMS | Implement content model: Assets/Gallery | Images, alt text, usage notes | P1 | Developer | 1 | Not Started | DEV-009 | Alt text required
DEV-052 | Sprint 4 - Forms CMS Analytics | CMS | Implement content model: Dealers or Installers | Installer/contact locations placeholder | P2 | Developer | 1.25 | Not Started |  | Can be disabled if not ready
DEV-053 | Sprint 4 - Forms CMS Analytics | Forms | Implement Contact form | Name, phone, LINE, message | P0 | Developer | 1.25 | Not Started | DEV-022 | Submission captured and notification sent
DEV-054 | Sprint 4 - Forms CMS Analytics | Forms | Implement Quote request form | Vehicle, service, product interest, contact | P0 | Developer | 1.5 | Not Started | DEV-022 | No price displayed after submit
DEV-055 | Sprint 4 - Forms CMS Analytics | Forms | Implement Dealer application form | Business info, location, experience, contact | P0 | Developer | 1.5 | Not Started | DEV-022 | Dealer lead routed separately
DEV-056 | Sprint 4 - Forms CMS Analytics | Forms | Implement Find Installer request | Area, vehicle, product interest | P1 | Developer | 1 | Not Started | DEV-022 | Lead can be routed to shop/admin
DEV-057 | Sprint 4 - Forms CMS Analytics | Forms | Configure anti-spam and rate limiting | Captcha/honeypot/rate limit | P0 | Developer | 0.75 | Not Started | DEV-053 | Spam protection active
DEV-058 | Sprint 4 - Forms CMS Analytics | Forms | Configure lead notification routing | Email/CRM/Sheet routing | P0 | Developer | 1 | Not Started | DEV-053 | Admin receives all test submissions
DEV-059 | Sprint 4 - Forms CMS Analytics | Analytics | Install analytics base tags | GA4 / pixels as confirmed | P0 | Developer | 0.75 | Not Started |  | Tags fire on staging only after consent decision
DEV-060 | Sprint 4 - Forms CMS Analytics | Analytics | Implement CTA click tracking | Data layer events | P1 | Developer | 0.75 | Not Started | DEV-013 | Get a Quote / Find Installer tracked
DEV-061 | Sprint 4 - Forms CMS Analytics | Analytics | Implement form submission tracking | Lead submit events | P1 | Developer | 0.75 | Not Started | DEV-053 | Success event fires once
DEV-062 | Sprint 4 - Forms CMS Analytics | SEO | Implement metadata templates | Title, description, canonical, OG tags | P0 | Developer | 1 | Not Started |  | Metadata present for all routes
DEV-063 | Sprint 4 - Forms CMS Analytics | SEO | Implement sitemap and robots rules | Sitemap.xml and robots.txt | P0 | Developer | 0.5 | Not Started | DEV-062 | Sitemap accessible
DEV-064 | Sprint 4 - Forms CMS Analytics | SEO | Prepare structured data | Organization, FAQ, public product schema | P1 | Developer | 1 | Not Started | DEV-062 | No pricing in schema
DEV-065 | Sprint 5 - QA Launch | QA | Run desktop visual QA against final reference | 1440px visual QA pass | P0 | QA | 1 | Not Started |  | Major layout differences logged
DEV-066 | Sprint 5 - QA Launch | QA | Run tablet and mobile responsive QA | 768px and 390px QA pass | P0 | QA | 1 | Not Started |  | No overflow/horizontal scroll
DEV-067 | Sprint 5 - QA Launch | QA | Run Thai text rendering QA | Thai line breaks and font check | P0 | QA | 0.5 | Not Started | DEV-006 | Thai text readable
DEV-068 | Sprint 5 - QA Launch | QA | Run no-price audit | Search all pages for price fields/symbols | P0 | QA | 0.5 | Not Started |  | No public pricing found
DEV-069 | Sprint 5 - QA Launch | QA | Run link and CTA audit | All internal/external links checked | P0 | QA | 0.5 | Not Started |  | No broken CTA
DEV-070 | Sprint 5 - QA Launch | QA | Run form submission tests | Contact/Quote/Dealer/Installer test leads | P0 | QA | 1 | Not Started | DEV-053 | All leads captured and routed
DEV-071 | Sprint 5 - QA Launch | QA | Run performance optimization pass | Image compression, lazy loading, cache headers | P0 | Developer | 1 | Not Started |  | Core pages meet agreed speed budget
DEV-072 | Sprint 5 - QA Launch | QA | Run accessibility baseline check | Keyboard, labels, alt text, focus states | P1 | QA | 1 | Not Started |  | Critical accessibility issues resolved
DEV-073 | Sprint 5 - QA Launch | QA | Run SEO readiness check | Metadata, sitemap, robots, structured data | P0 | QA | 0.75 | Not Started | DEV-062 | SEO checklist passed
DEV-074 | Sprint 5 - QA Launch | Security | Run security review | Forms, headers, admin access, backups | P0 | Developer | 0.75 | Not Started |  | No critical security issues
DEV-075 | Sprint 5 - QA Launch | Content | Final content review by owner | Owner approval on all pages | P0 | Project Lead | 1 | Not Started |  | Final copy approved
DEV-076 | Sprint 5 - QA Launch | Launch | Prepare launch plan | Launch window and rollback plan | P0 | Project Lead | 0.75 | Not Started |  | Launch checklist approved
DEV-077 | Sprint 5 - QA Launch | Launch | Connect domain and SSL | Production domain live with SSL | P0 | Developer | 0.75 | Not Started | DEV-076 | HTTPS works
DEV-078 | Sprint 5 - QA Launch | Launch | Production smoke test | Post-launch smoke test | P0 | QA | 0.75 | Not Started | DEV-077 | Forms, routes, analytics verified
DEV-079 | Sprint 5 - QA Launch | Handoff | Prepare admin training note | CMS/forms/analytics handoff | P1 | Developer | 1 | Not Started |  | Owner can update content
DEV-080 | Sprint 5 - QA Launch | Handoff | Prepare maintenance plan | Monthly maintenance checklist | P2 | Project Lead | 0.5 | Not Started |  | Maintenance owner assigned
DEV-081 | Sprint 0 - Setup | Forms / Routing | Apply v5.1 nexsppf contact and lead routing lock | All contact labels and routing destinations use nexsppf | P0 | Developer | 0.5 | Not Started | DEV-004 | Footer, contact page and all forms show/route to nexsppf; no mock contact data visible
DEV-082 | Sprint 0 - Setup | Assets | Apply v5.1 AI render launch decision | P0 asset source set to AI render for launch v1 | P0 | Designer | 0.5 | Not Started | DEV-009 | P0 hero/product/technology images generated or queued as AI renders; artifacts pass visual QA
DEV-083 | Sprint 0 - Setup | Stack / CMS | Apply v5.2 Next.js + Sanity stack lock | Project scaffold plan, package choices, Sanity workspace plan | P0 | Developer | 0.75 | Not Started | DEV-002 | Next.js / React / TypeScript / Tailwind CSS and Sanity are set as the production stack
DEV-084 | Sprint 0 - Setup | CMS | Create Sanity schema implementation backlog | Sanity schema list for pages, products, assets, FAQ, SEO, blog and leads | P0 | Developer | 0.5 | Not Started | DEV-002 | CMS content is structured and config-driven; no product price fields exist

## Sprint Plan
Sprint | Suggested Timing | Objective | Key Deliverables | Exit Criteria
Sprint 0 - Setup | Week 0 | Prepare repository, environments, tokens, content and asset map. | Repo, staging, tokens, content inventory, QA tracker. | Staging exists; final stack and no-price rule confirmed.
Sprint 1 - UI Foundation | Week 1 | Build reusable UI system before page production. | Header, nav, buttons, hero, cards, forms, tables, FAQ. | All components pass desktop/mobile smoke test.
Sprint 2 - Core Pages | Week 2 | Build homepage and brand pages. | Homepage, About, Technology, FAQ, Contact shell. | Core pages review-ready with real copy.
Sprint 3 - Product System | Week 3 | Build Clear, Matte, Color and Compare pages. | 12 film options, public tables, product cards. | No pricing fields; all product names correct.
Sprint 4 - Forms CMS Analytics | Week 4 | Make content editable and connect lead capture. | CMS, forms, routing, analytics, SEO metadata. | Leads captured; admin can update content.
Sprint 5 - QA Launch | Week 5 | Stabilize, optimize and launch. | QA reports, fixes, deployment, handoff. | Production live and smoke test passed.

## Routes
Route | Page | Template | Primary CTA | SEO Focus | CMS Driven | Notes
/ | Homepage | Landing | Explore Film Systems / Get a Quote | NEXS automotive film, PPF, color PPF | Partial | Must retain white Apple-style theme.
/clear-ppf | Clear PPF | Product Category | Get a Quote | clear PPF, paint protection film | Yes | 4 tiers: Begin/Prime/Pro/Ultimate.
/matte-ppf | Matte PPF | Product Category | Book Consultation | matte PPF, satin film | Yes | 3 tiers: Matte Prime/Pro/Ultimate.
/color-ppf | Color PPF | Product Category | Explore Colors / Get a Quote | color PPF, wrap, carbon fiber PPF | Yes | 5 tiers with Ultimate Carbon Fiber.
/technology | Technology | Content | Compare Film Systems | TPU film, self-healing PPF, hydrophobic film | Partial | No unsupported lab claims.
/compare | Compare | Comparison | Talk to an Expert | compare PPF products | Yes | No pricing.
/for-dealers | For Dealers | Lead Page | Apply as Dealer | PPF dealer, installer program | Partial | Dealer lead routing separated.
/about-nexs | About NEXS | Brand Page | Explore Products | NEXS brand, automotive surface technology | Partial | Use brand story copy.
/faq | FAQ | FAQ | Contact Us | PPF FAQ Thailand | Yes | FAQ schema-ready.
/contact | Contact | Contact | Send Inquiry | contact NEXS | Partial | Real contact data required before launch.

## Components
Component | Used On | Data Source | States | Notes
Header / Navigation | All pages | Static + CMS optional | Desktop, mobile, sticky, active | Global nav must be consistent.
Hero Block | Home/Product/About/Technology | Page content | Image left/right, CTA variants | White/grey canvas; avoid full black hero.
Product Group Card | Home, Compare | Product categories | Default, hover, selected | Shows Clear / Matte / Color summary.
Product Tier Card | Product pages | Products model | Default, featured, disabled | No prices, no internal specs.
Comparison Table | Product and Compare pages | Public specs | Desktop table, mobile cards | No pricing schema.
Technology Card | Home/Technology | Technology content | Icon/image/text | Avoid unsupported claims.
Quote Block | Home/About/Product | Static content | Dark panel | Only controlled black section.
FAQ Accordion | FAQ/Product pages | FAQ model | Open/closed/focus | Accessible keyboard interaction.
Lead Form | Contact/Quote/Dealer | Forms config | Input/error/success/loading | Spam protection required.
Gallery / Carousel | Product/About | Assets model | Lazy loaded | Use asset tracker IDs.
Footer | All pages | Static + contact | Default | Real contact data before launch.

## CMS Models
Sanity Model | Purpose | Key Fields | Public/Private | Validation / Rule
Page | Editable marketing pages | title, slug, seoTitle, seoDescription, sections, heroImage | Public | Slug unique; no pricing fields.
ProductCategory | Clear/Matte/Color grouping | name, slug, tagline, hero, products, FAQs | Public | Exactly 3 active categories for initial launch.
Product | 12 public film options | name, category, tier, positioning, finish, warrantyText, publicSpecs, CTA | Public | No price, dealer cost, supplier, roll price.
ProductSpec | Public comparison data | label, value, productId, sortOrder | Public | Approved public specs only.
FAQ | Question and answer content | category, question, answer, sortOrder | Public | FAQ schema-ready copy.
Asset | Images and render assets | assetId, title, alt, pageUsage, ratio, status | Public | Alt text required.
BlogPost | Future article / knowledge content | title, slug, excerpt, body, seo, coverImage | Public optional | Can be disabled at launch if not ready.
Lead | Captured form submissions | formType, contactInfo, productInterest, message, source, status | Private | Never exposed publicly.
DealerApplication | B2B dealer leads | businessName, location, experience, contact, notes, status | Private | Access limited to admin.
InstallerLocation | Future find installer feature | name, province, contact, products, active | Public optional | Can launch disabled if not ready.

## Forms
Form | Location | Fields | Required Fields | Routing | Tracking Event | Success State
Contact | /contact + footer CTA | name, phone, LINE, email, message | name, phone/message | nexsppf lead channel / CRM-Sheet destination | lead_submit_contact | Thank you; team will contact soon.
Quote Request | Product pages + homepage | name, phone, LINE, vehicle, product interest, service location, message | name, phone, product interest | nexsppf sales lead channel / CRM-Sheet destination | lead_submit_quote | Inquiry received; no price shown.
Dealer Application | /for-dealers | business name, owner name, province, phone, LINE, experience, current services, message | business name, province, phone | nexsppf dealer lead channel / CRM-Sheet destination | lead_submit_dealer | Application received; team will review.
Find Installer Request | Product pages / future find installer | name, phone, province, vehicle, product interest | name, phone, province | nexsppf installer lead channel / CRM-Sheet destination | lead_submit_installer | NEXS team will recommend installer.

## Analytics
Event | Trigger | Parameters | Used For | Priority
page_view | Every route load | page_path, page_title, language | Traffic baseline | P0
cta_click | CTA button click | cta_label, page_path, destination | CTA performance | P0
product_card_view | Product cards visible | category, product_tier | Product interest | P1
product_compare_view | Compare table visible | category | Comparison behavior | P1
lead_submit_contact | Contact form success | source_page, form_type | Lead tracking | P0
lead_submit_quote | Quote request success | source_page, product_interest | Sales lead tracking | P0
lead_submit_dealer | Dealer form success | province, experience_level | B2B lead tracking | P0
line_click | LINE CTA click | page_path, cta_label | LINE conversion | P0
faq_open | FAQ item opened | faq_category, question_id | Content optimization | P2
asset_gallery_interaction | Gallery/carousel interaction | asset_group, page_path | Visual content performance | P2

## SEO QA
Category | Checklist Item | Owner | Status | Notes
Metadata | Unique title and meta description for every route | Developer | Not Started
Metadata | Open Graph image and copy set | Developer | Not Started
Canonical | Canonical URL on all public pages | Developer | Not Started
Sitemap | sitemap.xml generated and accessible | Developer | Not Started
Robots | robots.txt configured for production | Developer | Not Started
Structured Data | Organization schema without pricing | Developer | Not Started
Structured Data | FAQ schema for FAQ page and category FAQs | Developer | Not Started
Images | Alt text for all key images | Content Admin | Not Started
Thai SEO | Thai keyword copy preserved; no AI gibberish | Content Admin | Not Started
Performance | Hero images optimized and responsive | Developer | Not Started
No Price | No price fields in metadata/schema/content | QA | Not Started | Critical.

## Launch Checklist
Category | Checklist Item | Owner | Status | Evidence / Link
Content | All copy approved by owner | Project Lead | Not Started
Content | No public pricing anywhere | QA | Not Started
Content | Real contact information inserted | Content Admin | Not Started
Assets | P0 images replaced with final assets | Designer | Not Started
Assets | No watermark/stock marks/AI artifacts visible | QA | Not Started
Forms | Contact form test passed | QA | Not Started
Forms | Quote request test passed | QA | Not Started
Forms | Dealer application test passed | QA | Not Started
Analytics | Analytics events tested | Developer | Not Started
SEO | Sitemap and robots tested | Developer | Not Started
Performance | Core pages optimized | Developer | Not Started
Security | Admin access locked down | Developer | Not Started
Deployment | Domain and SSL connected | Developer | Not Started
Deployment | Rollback plan documented | Project Lead | Not Started
Post Launch | Production smoke test completed | QA | Not Started

## Risks Decisions
Type | Item | Impact | Recommendation | Decision / Owner
Decision | Final build stack | Affects development speed and maintenance | Use custom frontend + CMS for premium control; WordPress custom theme if admin simplicity is more important. | LOCKED v5.2: Next.js / React / TypeScript frontend with Tailwind CSS, Sanity CMS, GitHub Actions CI/CD, optimized image storage/CDN, and API-backed or third-party form handling.
Decision | CMS vendor or admin system | Affects content editing and cost | Choose before Sprint 0 starts. | LOCKED v5.2: Sanity CMS is the recommended CMS. Strapi and Payload remain fallback options only if project constraints change.
Decision | Lead destination | Affects forms and operations | Confirm email inbox, CRM, Google Sheet, or LINE routing. | LOCKED v5.1: route all public lead forms to nexsppf; exact email/webhook/API connected during Sprint 0.
Decision | Full bilingual site or Thai-primary site | Affects copy and routing | Launch Thai-primary with English brand lines; prepare bilingual CMS if needed. | Project Lead
Decision | Real contact data | Cannot launch with mock contact details | Provide official phone, LINE, email, address, social links. | LOCKED v5.1: use nexsppf across public contact channels; no public phone/address until separately confirmed.
Risk | AI-generated images used as final assets | Possible artifacts or inconsistent vehicle details | Use AI renders only after QA; replace dealer/installer images with real photography. | LOCKED v5.1: launch P0 visual assets use AI render; QA artifacts before publishing; real dealer/installer photos become Phase 2.
Risk | Dev interprets mockups as exact text source | AI text may be distorted | Use copy lock document only. | Project Lead
Risk | Public pricing accidentally leaks through product data | Commercial risk | Exclude price fields from public CMS/templates/schema. | Developer
Risk | Full black theme returns during build | Breaks approved Apple-style direction | Use v4 tokens and white canvas default. | Designer/Developer
Risk | Product warranty values not final | Content inconsistency | Use warranty up-to phrasing until confirmed. | Content Admin
Decision | WordPress custom theme | Possible but not primary option | Use only if client specifically requires WordPress editorial workflow. | LOCKED v5.2: not recommended as primary production path.

## Sprint0 Lock v5.2
NEXS Sprint 0 Decision Lock v5.2
Decision Date | 2026-05-13
Scope | Final stack / CMS + contact channels + lead routing + AI render launch decision
Locked Item | Final Value | Implementation Rule | Notes
Global contact handle | nexsppf | Use nexsppf as the contact identity across public channels. | No alternate handle in public UI.
LINE Official | nexsppf | Footer/contact/social/contact form reference uses nexsppf. | Add exact OA link during Sprint 0.
Facebook | nexsppf | Display and social slug use nexsppf. | URL to be connected by developer.
Instagram | @nexsppf | Display @nexsppf. | Use same handle across site.
TikTok | @nexsppf | Display @nexsppf. | Use same handle across site.
YouTube | @nexsppf | Display @nexsppf. | Use same handle across site.
Threads / other social | @nexsppf | Display @nexsppf where the platform supports @ format. | Optional channel.
Email display | nexsppf | Use nexsppf as temporary contact identity until exact email is provided. | Do not invent domain.
Lead routing | nexsppf | All forms route to nexsppf destination label / inbox / CRM sheet. | Exact webhook/API/email connected in Sprint 0.
Homepage CTA | Get a Quote / Talk to NEXS | CTA routes to contact/quote form with nexsppf destination. | No pricing displayed.
Image source for launch | AI render | P0 hero/product/technology visuals use AI render for launch v1. | Real dealer/installer photography can replace later.
Dealer/installer images | AI render launch / real photo Phase 2 | Use AI render or controlled placeholder at launch; swap to real photography when available. | Avoid fake faces/brands/plates.
Public pricing | No public pricing | Do not display price, starting price, Base/XL/XXL, supplier cost, dealer price. | Rule remains locked.
Frontend stack | Next.js / React / TypeScript | Build the public website as a custom frontend, not a template site. | Use app/router structure chosen by dev team.
Styling | Tailwind CSS | Use v4 design tokens as Tailwind theme inputs. | Keep white Apple-style canvas; do not revert to all-black theme.
CMS | Sanity CMS | Use Headless CMS for editable pages, products, campaign copy, blog, SEO and media. | Strapi/Payload are fallback only if constraints change.
Deployment | GitHub Actions CI/CD | Use CI/CD for staging and production deployment. | Hosting should be static/edge-friendly based on final provider.
Media | Optimized image storage/CDN | Serve AI render assets through optimized image pipeline/CDN. | Use WebP/AVIF where appropriate.
Forms / Leads | API-backed or third-party form service | Forms must route to nexsppf destination and be protected by anti-spam. | No price shown after submit.
Config rule | CMS/config-driven content | Product specs, labels, navigation, SEO, campaign copy and media should not be hardcoded. | Hardcode only stable layout/component logic.
Open Decision Remaining | Bilingual depth | Thai-primary vs full bilingual still needs final operation decision. | English brand lines already included.
Open Decision Remaining | Exact platform links / URLs | Handle is locked as nexsppf, but exact URLs and OA links must be entered during Sprint 0. | Do not invent domain/email.